BA Hackathon

Playbook

This playbook is for use by IIBA Chapters only

and shall not be made publicly available.

TABLE OF CONTENTS

1	Introduction and Purpose	3

2	Project Setup	3

3	BA Hackathon Definition	4

4	BA Hackathon Design Brief	5

5	Preliminary Analysis	5

6	Communications	5

7	Non-Disclosure Agreement and Media Release Form	6

8	Logistics	6

8.1	Catering	7

9	Registration and Tracking	7

9.1	Registration	7

9.2	Participant and Volunteer Tracking	7

10	Event	8

10.1	Setting up the Team Tables	8

10.2	Conducting the Event	8

11	Post-Event	9

12	Final Steps	9

# Introduction and Purpose

A BA hackathon is an amazing way to provide learning, networking and mentorship opportunities while doing some actual BA work. In December 2019, IIBA Ottawa-Outaouais piloted a BA hackathon called “BA Blitz”. The focus of this hackathon was about giving back to the community by leveraging the local BA community.  A team of BA participants (with facilitation by IIBA Ottawa-Outaouais Chapter) got together on a Saturday and performed some pro bono BA work for a Canadian non-profit organization, Women’s Economic Council.

Since this was the first significant IIBA BA hackathon of its kind, we learned a few lessons along the way.  We also had to create some project artifacts from scratch. This playbook provides guidance and tools for IIBA Chapters to use if they choose to run their own BA hackathons.  Please use the elements that work for you and your community.

# Project Setup

The project team can be kept relatively small.  The following is a suggested composition:

- PM – 1

- Hackathon committee – 3

- Sr. BAs – 2.  These BAs can also be part of the committee and/or hackathon participants if they wish.

- Communications - 1

From the non-profit organization (NPO), you will need about 3 people with the following knowledge and time availabilities:

- Knowledge about the NPO’s history

- Knowledge about the NPO’s strategy (mission, vision)

- Knowledge about the NPO’s business problems and opportunities

- Willingness to speak on behalf of the NPO

- Time to meet (4-5 planning meetings online or in-person)

- Ability to attend the event to provide information to the teams

- Time to meet to review the results

The following RACI chart provides an outline of the resources that you will need:

| HIGH-LEVEL TASKS | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Definition of BA Blitz event, success criteria, client selection criteria, fee structure | PM, Chapter Board or committee | PM | Chapter Board |  |
| Prepare budget | PM, Chapter Board or Committee | PM | Chapter Board |  |
| Visit 3 non-profit orgs. Select 1 org. | Committee | PM |  | Chapter Board |
| Preliminary problem definition with the client org | Sr. BAs, NPO | PM |  | Chapter Board |
| Identify target BAs, marketing the event | Committee, Communications | Committee | NPO | Chapter Board |
| Provide NPO’s NDA | NPO | NPO | Committee |  |
| Prepare media release form | Committee, Communications | Committee | NPO | NPO, Chapter Board, PM |
| Track participant registrations, signing of NDA and media release forms | Committee | Committee |  | NPO, Chapter Board, PM |
| Identify the NPO participants | NPO | NPO | Committee | Chapter Board, PM |
| Logistics (date, time, room, food, supplies, equipment) | Committee | Committee | NPO | Chapter Board, NPO |
| Shop for, purchase, expense Swag | Committee | Committee |  |  |
| Event Day - check-in, welcome, team assignments | Committee, NPO | Committee |  |  |
| Event Day - BABOK, theory discussion | Committee | Committee |  |  |
| Event Day - Facilitation, problem clarification | Committee, NPO | Committee |  |  |
| Event Day - Conduct Business Analysis, Present BA work | Participants | Committee |  |  |
| Event Day - Closing | Committee, NPO | Committee |  |  |
| Post-Event - Lessons Learned, Update procedures, cost/revenue calculation | Committee, NPO | PM |  | Chapter Board |
| Post-Event - Publish | Committee, Communications | Committee |  | Chapter Board |
| Post-Event - Follow-up with NPO | Committee, NPO | PM |  |  |

# BA Hackathon Definition

Because the hackathon idea and business analysis may be foreign to some organizations, IIBA Ottawa-Outaouais Chapter prepared a flyer describing the event and its benefits.  You can use the attached template – please edit the text as you see fit.  It is recommended that you PDF it before you distribute it to any NPOs.

# BA Hackathon Design Brief

Once you have chosen an NPO to partner with, it is recommended that you draft a Design Brief, similar to a Statement of Work but less formal.  The purpose of the Design Brief is to set expectations on the project management of the hackathon, the running of the hackathon and which party is doing what.

Attached is a sample Design Brief template. Please edit this as required.

# Preliminary Analysis

It is important to do some preliminary analysis with the NPO. We had 2 Sr. BAs attend a couple of conference calls with the NPO to learn about the organizations and what are some of the top business problems they faced.  We selected 3 business problems that would be good candidate problems for the BA hackathon – problems that lend themselves to business analysis (e.g. Could be modeled) and that we felt that the BAs could come up with solutions to these problems in the one day.

After the first conference call with the NPO, the Sr. BAs regrouped and planned how to write a short case study.  The intent was to draft a cast study for the NPO’s approval and then to send the case study to the hackathon participants one week prior to the event so that they could familiarize themselves with the problem.

Below is a sample Case Study template.  Please edit as required.

# Communications

In terms of external communications there are several objectives:

- Promote the value of the BA profession

- Promote the NPO

- Promote your Chapter

- Promote the event, create hype and attract registrations, volunteers and sponsors.  For the registrants, you want to attract BAs at varying experience levels (senior, intermediate and novice).   You should have at least 1 senior per team.  When setting up the event, you may want to target 20-25 BA participants.  Any more than that will be hard to manage. Also be mindful of the venue capacity.

You may want to have a point person who can answer any questions from your audiences.  The following are some sample communications.  Please edit as required.

For your Chapter website:

You should prepare similar communications in your online registration tool (if using).  The IIBA Ottawa-Outaouais example is as follows:

Other places to promote:

- Your workplace

- Your other Chapter events (allocate about 5 minutes to cross-promote events)

- Anywhere that there are Senior, Intermediate and Novice BAs

- Social media (LinkedIn, Twitter).  Also ask some influencers to like/comment/share your posts.

# Non-Disclosure Agreement and Media Release Form

Non-Profits are sensitive to revealing their private information. In order to be able to perform business analysis while addressing their privacy concerns, you should ask the NPO to provide a copy of THEIR non-disclosure agreement form.

Instruct the hackathon participants to sign and return the form to you before sharing any sensitive or private information with them. This includes the case study.  (In the IIBA Ottawa-Outaouais case, we planned to send the case study to the participants one week prior to the hackathon in order to allow them to familiarize themselves with the NPO’s background. We required the participants to sign and return the NDA before sending each one of them the case study; this also allowed us to really confirm that they were committing to participating.)

It is also good to be able to celebrate and publicize the fact that your Chapter ran the hackathon.  When planning to use photos, videos, interviews or names of the participants, you need to ask them to sign a Media Release Form.  This form can be completed by the participants either before the event or the day of the event.

You can take lots of pictures/videos during the event day.  Just review the image and video files and rename them to “Do not use.xxx” for any of the ones that contain people that didn’t want to have their pictures/videos publish.  Or you can crop out those people in whatever you publish.

Keep the signed forms in your records. Send the signed NDAs to the NPO for their records as well.

Go to Section 9.1 for a tracking spreadsheet template.

# Logistics

It is highly recommended that you do a site visit at least one week prior to the event.  The following are some of the details you should plan:

- Whether you are allowed to rearrange furniture. (Tip: take a picture of the original layout in case the host wants to you put it back the way it was afterward.)

- How you want to set up the teams

- How to access the building, particularly if the event outside of business hours

- Are you allowed to bring in your own catering or do you have to use the host’s caterer

- How you will bring in food/drink – is there a loading area, are there elevators to the room

- Do you need a projector, blank wall, power bars, extension cords, whiteboard

- What office supplies will the host provide

- Where will your photographer set up (if using one)

- Where will you set up the food

- Wifi information, if available

- Process flow for how the participants will enter the room, check-in, get food and pick a table

The following is a sample floor plan from the IIBA Ottawa-Outaouais BA Blitz to give you an idea of the details to share with the volunteers for that day:

## Catering

- Determine where you are going to get food from and who is paying what portion (your Chapter versus the NPO).

- Be mindful of any food allergies or restrictions.

- You may want to have hot tea and coffee throughout the day.

# Registration and Tracking

## Registration

For IIBA Ottawa-Outaouais’ BA Blitz, we an online tool to facilitate registration. We set up three ticket types for the participants (Novice, Intermediate and Senior) all at the same price. The ticket price was $25 – a moderate price to ensure that people would commit to showing up but not so high because we didn’t want the participants to feel like they were paying a fee for providing their own service. We monitored incoming registrations to make sure we had enough Senior BAs (at least one per team) so that the BA teams would be effective. We also set up a hidden ticket type, enabled by a promo code for the volunteers.  We sent periodic email updates to:

- Remind participants to submit the NDA

- Remind people of the event date and logistics

- Inform them of any important information and updates about the event

We made sure to take attendance for our records for PD/CDU purposes.

Because this event was very popular, it sold out quickly. We used the online tool’s waitlist functionality to issue tickets to people on the waiting list when others cancelled.

## Participant and Volunteer Tracking

The NDA is a mandatory document that needs to be completed by the participants prior to participating.  The Media Release Form need to be completed at the very latest, the day of the event.  You also need to track any specific dietary restrictions/food allergies for catering.

You can use the following spreadsheet to track the completion of the forms and food info:

Once each participant returns their signed NDA, you can send them the case study. (Or you can send the case study to all participants (who signed the NDA) at the same time, e.g. one week before the event.)

# Event

## Setting up the Team Tables

It is useful to set up one team per business problem.  And within each team, make sure there is at least one Senior BA so that they can provide mentorship to the team in using different techniques.  The following are some steps that will help you organize the teams.

- Plan for about 3-4 tables, each table with a team of 5-7 people.

- Put “S”, “I”, “N” place cards (folded index cards or tent cards) at each seat.  When attendees arrive, note which BA level they registered as (Senior, Intermediate, Novice) and instruct each one to sit at a spot that had a corresponding place card.

- Place a couple of printed copies of the Case Study at each table for reference.

- Place a blank Techniques Use form at each table.  It will be useful to learn and demonstrate all the techniques that the BAs practiced for the NPO. (See sample below)

- Make other supplies available to the participants (flip chart paper, sticky notes, markers, tape, blank paper, dot stickers)

## Conducting the Event

Start the event with some opening remarks.  You may want to have a slide deck prepared.  Include your Chapter logo and the NPO’s logo.  Include the agenda for the day.  Also, you can cross-promote for other events that your Chapter will be holding.

The following is a sample high-level agenda:

- Opening remarks (your Chapter)

- About the NPO (the NPO)

- How the hackathon will work (your Chapter). This is where you show the BABOK and talk about the 6 Knowledge Areas and 50 techniques that the teams may wish to refer to when doing their work. Emphasize that the teams must come up with solutions (don’t just stay in requirements).

- Make sure to instruct the participants to write down their solutions.  This is crucial since the NPO needs to be able to walk away with the solutions and implement some of them later on.

- Start the hackathon.

- Lunch – teams may wish to work through lunch

- Continue hackathon.

- Last hour of the day – teams present how they went about performing BA work and present a couple solutions they came up with

- Ask people to provide their feedback on the event. This can be done on flipcharts where people write their comments on sticky notes.  You may want to have a “Happy Face” sheet and a “Sad Face” sheet where people can stick their stickies about what they liked/didn’t like about the event. (Or you can do an online survey but the response rate might be low.)

- Thank you remarks, certificate presentations (if they are printed)

Tips:

- It is extremely valuable to have representatives from the NPO present in order to answer questions from the teams.

- Amongst your volunteers, you may wish to have a couple of senior BAs who can walk the room and provide guidance in case anyone has questions about how to apply the techniques.

- You may want to have a photographer/videographer take pictures and videos and interviews throughout the day. It may also be useful to “stage” some pictures and videos in order to get the best camera angles.

- After the event wraps up, you should collect all the BA artifacts (flip charts, whiteboard pics, techniques worksheets, etc.). Inform the NPO that you will compile the results into a summary report for them.

- Take pictures of all the flipcharts and whiteboards so that you don’t lose them.

# Post-Event

Schedule a review meeting between the hackathon committee and the NPO.  This can be done online or in person.

Prepare a summary report which should include the following sections:

- Notes, techniques, recommendations and solutions from each team and which business problem they tackled

- Pictures of BA artifacts

- Feedback about the event

When you meet with the NPO to review the summary report, you can discuss a recommended action plan – which the NPO will ultimately own and be responsible for.  The Action Plan can be a table like the one below:

| Business Objectives (from the NPO’s strategic plan) | Actions (use recommendations from BA hackathon) | Success Criteria (How will the NPO know if NPO was successful in achieving the objectives?) | Gaps/Constraints (What are the gaps, constraints that might inhibit the NPO from performing the actions?) |
| --- | --- | --- | --- |

# Final Steps

- Finalize expenses.

- Publish and celebrate the results of your event. (Be mindful of any private information that the NPO doesn’t want to publish.)

- Document the steps you followed.

- Save any hackathon templates and artifacts within your Chapter’s repository so that you can repeat the event in the future.

- Conduct a lessons-learned session within your own Chapter.